## Slide 1: DevNet Learning Forum
0 - Kickoff

## Slide 2: Agenda
To Know Each Other
DevNet Incubation Plan
About the Forum

## Slide 3: To Know Each Other

## Slide 4: Self-intro in JSON

## Slide 5: Who’s Next?
Copy json file to your computer
Modify with your own data
Upload it to github/ email to me
Check it out soon!
$ git clone https://github.com/tqs0117/devnet_forum.git
https://github.com/tqs0117/devnet_forum/blob/1st_forum/0.kickoff/namelist/namelist.json

## Slide 6: DevNet Incubation Plan

## Slide 7: DevNet Incubation
Phase-1: DevNet Learning Forum
  ENTG-Wide & Interest-Based
  Fundamental Training & Self-paced Learning
  Certification – DevNet Professional (available on Feb.24)
Phase-2
  Group-Based Study & Coding
  Contribution to Automation Tools & Cases
  Contribution to DevNet CodeX, Community & Activities

## Slide 8: DevNet Learning Forum
To build capability to support customers and partners in software API and automation
All participators pass DevNet Professional Exam
Target
The forum will be launched in FY20Q3.
The forum takes 5 weeks* to cover following agenda
  DevNet Introduction and Environment Setup
  Programming Fundamentals
  Network APIs
  Guestshell and App-hosting
  DevOps Introduction
Execution
The forum focus on incubation of NetDevOps engineers for EN and Korea Support Services team.
This is an interest-based forum and participators need to pay extra time on learning and practices.
Participators will be required to enroll DevNet Professional Exam
Strategy
* 1-2 2hrs sessions each week

## Slide 9: DevNet Learning Forum
FY20Q3
Today
Feb
Mar
Apr
6 days
17 days
Mgmt. Review
Feb 17- Feb 28
24 days
Content Review
Feb 12- Mar 3
16 days
5weeks‘ forum
Mar 9- Apr 10
25 days
Presentation to
all managers
Feb 24
Kickoff
Mar 4
Nov 7
Dec 20
Presentation to
all managers
tbd
Wrap-up &
Recognition
Apr 15
Timeline
Participants
Nominate by ENTG Managers
Expertise in any of Cisco Product Line is MUST
Knowledge of any Programming Language is Recommended
SME is Encouraged to join the 1st forum

## Slide 10: About the Forum

## Slide 11: Slogan
Learn a bit
Get a certificate
Have a lot of fun

## Slide 12: Speaker
Week1: Frank
Week2: TBD
Week3: TBD
Week4: TBD
Week5: TBD

## Slide 13: Agenda
Week1
  DevNet Introduction
  Dev Environment Setup
Week2
  Data Models
  Python for Network
Week3
  Yang, Netconf, Restconf
  Network Device API
Week4
  Guest Shell
  Application Hosting
Week5
  DevOps
  Ansible
At Every
Tuesday 4-5:30 pm
  30mins practices
  60mins lecture
Thursday 4-5:30 pm (if need)

## Slide 14: Get Started
Learn network programmability basics (DevNet Video Courses)
  https://developer.cisco.com/video/net-prog-basics/
Developer Workstation and Environment Setup (Step-by-Step Guide)
  https://developer.cisco.com/learning/modules/dev-setup
ENT DevNet Portal (under dev.)
  https://cisco.sharepoint.com/sites/ent_devnet
Python Tutorial
  https://www.learnpython.org/

## Slide 15: Let’s check it out!